## Phase Summary
Phase | Name | Complexity | Hours (Low) | Hours (High) | Duration | Dependencies | Status | Notes
1 | Foundation & Data Intelligence | Medium | 120 | 160 | 3-4 weeks | None | Not Started | Enables all subsequent phases
2 | Learner Intelligence Engine | Heavy | 200 | 280 | 5-7 weeks | Phase 1 | Not Started | Can run parallel with Phase 3
3 | Content Intelligence Pipeline | Heavy | 240 | 320 | 6-8 weeks | Phase 1 | Not Started | Can run parallel with Phase 2
4 | Path Engine & Coach Tools | Heavy | 280 | 360 | 7-9 weeks | Phase 2, 3 | Not Started | Largest phase - core value delivery
5 | Analytics, Adaptation & Learner AI | Medium-Heavy | 240 | 320 | 6-8 weeks | Phase 4 | Not Started | Closes the feedback loop
| TOTAL |  | 1080 | 1440 | 22-30 weeks* |  |  | *Phases 2 & 3 parallel

## Capability Tracker
ID | Capability | Category | Phase | Complexity | Hours (Est.) | Priority | Status | Acceptance Criteria | Notes
C01 | Data Model Analysis | Foundation | 1 | Light | 20-30 | P0 | Not Started | Complete schema documentation of all tables, relationships, and data flows
C02 | Content Taxonomy Mapping | Foundation | 1 | Light | 15-20 | P0 | Not Started | Journey > Chapter > Lesson > Slide hierarchy mapped with all 68 slide types
C03 | EPP Integration Architecture | Foundation | 1 | Medium | 30-40 | P0 | Not Started | Criteria Corp EPP data parseable into structured personality dimensions
C04 | Database Schema Extensions | Foundation | 1 | Medium | 25-35 | P0 | Not Started | New tables for profiles, tags, recommendations, overrides, reassessments created
C05 | Infrastructure Setup | Foundation | 1 | Medium | 30-40 | P0 | Not Started | AI engine, API layer, secure credential management operational
C06 | EPP Profile Parser | Learner Intelligence | 2 | Medium | 30-40 | P0 | Not Started | 25 personality dimensions extracted and normalized from raw EPP data
C07 | Profile Interpretation Engine | Learner Intelligence | 2 | Heavy | 50-70 | P0 | Not Started | AI generates narrative profiles with strengths, gaps, tension pairs
C08 | Motivation Cluster Analysis | Learner Intelligence | 2 | Medium | 25-35 | P1 | Not Started | Motivation drivers classified from Q&A (intrinsic/extrinsic/mixed)
C09 | Learning Style Inference | Learner Intelligence | 2 | Medium | 20-30 | P1 | Not Started | Preferred learning modality determined from traits + behavior
C10 | Tension Pair Detection | Learner Intelligence | 2 | Medium | 20-30 | P1 | Not Started | Significant trait combos identified (e.g., high Achievement + low SelfConfidence)
C11 | Batch Profiling (400+ learners) | Learner Intelligence | 2 | Medium | 25-35 | P0 | Not Started | All EPP-assessed learners processed with <5% error rate
C12 | Learner Feedback Loop | Learner Intelligence | 2 | Light | 15-20 | P1 | Not Started | 'Not like me' buttons functional, feedback stored and actionable
C13 | Profile Versioning | Learner Intelligence | 2 | Light | 15-20 | P2 | Not Started | Profile history tracked across reassessments
C14 | AI Content Tagging Pipeline | Content Intelligence | 3 | Heavy | 60-80 | P0 | Not Started | 15-field extraction per lesson with trait associations, difficulty, style
C15 | Multi-Pass Confidence Scoring | Content Intelligence | 3 | Medium | 30-40 | P0 | Not Started | Two independent analyses per lesson with agreement score
C16 | Confidence-Gated Review | Content Intelligence | 3 | Medium | 25-35 | P0 | Not Started | Auto-approve >75%, review queue for <50%, pending for middle range
C17 | Content-Trait Mapping | Content Intelligence | 3 | Medium | 25-35 | P0 | Not Started | Each lesson tagged with builds/leverages/challenges per EPP dimension
C18 | Semantic Content Search (RAG) | Content Intelligence | 3 | Heavy | 40-50 | P1 | Not Started | Vector embeddings enable meaning-based lesson discovery
C19 | Review Queue Interface | Content Intelligence | 3 | Medium | 25-35 | P0 | Not Started | Coach/admin UI to approve, correct, or dismiss AI tags
C20 | Coaching Prompt Generation | Content Intelligence | 3 | Light | 15-20 | P2 | Not Started | AI-generated discussion starters per lesson
C21 | Bulk Content Processing | Content Intelligence | 3 | Medium | 20-30 | P0 | Not Started | All 90 lessons tagged in batch with audit trail
C22 | Content-Learner Matching Algorithm | Path Engine | 4 | Heavy | 50-60 | P0 | Not Started | Cosine similarity scoring with trait-weighted matching
C23 | Pedagogy Mode Configuration | Path Engine | 4 | Medium | 20-30 | P0 | Not Started | Gap-fill (70/30), Strength-lead (30/70), Balanced — per organization
C24 | Intelligent Sequencing & Diversity | Path Engine | 4 | Heavy | 40-50 | P0 | Not Started | Max 3 same-journey consecutive, diminishing returns, gap/strength interleave
C25 | Discovery Phase Logic | Path Engine | 4 | Medium | 15-20 | P1 | Not Started | First 3-5 lessons marked exploratory with softer framing
C26 | 20-Lesson Roadmap Generation | Path Engine | 4 | Medium | 25-35 | P0 | Not Started | Complete path with scores, rationale, trait coverage per item
C27 | Match Rationale Engine | Path Engine | 4 | Medium | 20-30 | P1 | Not Started | Human-readable explanation for every recommendation
C28 | Coach Workspace UI | Coach Tools | 4 | Heavy | 40-50 | P0 | Not Started | Search learners, view profiles, manage paths — dedicated interface
C29 | Coach Curation (Reorder/Swap/Lock) | Coach Tools | 4 | Medium | 30-40 | P0 | Not Started | Drag-and-drop path editing that persists through re-rankings
C30 | Coach Compatibility Signals | Coach Tools | 4 | Medium | 20-30 | P1 | Not Started | Green/Yellow/Red traffic light for coach-learner fit
C31 | Divergence Detection | Coach Tools | 4 | Light | 10-15 | P2 | Not Started | >30% coach-modified paths flagged as 'coach insight'
C32 | Curator AI Copilot | Coach Tools | 4 | Heavy | 40-50 | P1 | Not Started | Conversational AI for coaches to explore learner data and get suggestions
C33 | HR Cohort Dashboard | Analytics | 5 | Heavy | 40-50 | P0 | Not Started | Organization-wide learner progress, phases, metrics
C34 | EPP Heatmaps | Analytics | 5 | Medium | 20-25 | P1 | Not Started | Visual trait distribution across organization
C35 | Engagement Funnels | Analytics | 5 | Medium | 20-25 | P1 | Not Started | Learner progression stages with drop-off analysis
C36 | Content Effectiveness Analytics | Analytics | 5 | Medium | 15-20 | P2 | Not Started | Which lessons drive most engagement, ratings, saves
C37 | Quarterly Reassessment Engine | Adaptation | 5 | Heavy | 35-45 | P0 | Not Started | Scheduled EPP retakes with drift detection and path re-ranking
C38 | Mini-Assessment System | Adaptation | 5 | Medium | 25-35 | P1 | Not Started | 3-5 question mid-journey check-ins
C39 | Passive Signal Monitoring | Adaptation | 5 | Medium | 25-35 | P1 | Not Started | Engagement pattern aggregation triggers adaptive re-ranking
C40 | AI Companion Chat | Learner Experience | 5 | Heavy | 50-60 | P1 | Not Started | Conversational AI with teach/quiz/reflect/prepare/celebrate modes
C41 | Content 360 View | Analytics | 5 | Medium | 20-25 | P1 | Not Started | Detailed lesson intelligence: traits, difficulty, slides, coaching prompts
C42 | Algorithm Observability Dashboard | Platform | 5 | Medium | 15-20 | P2 | Not Started | Formulas, thresholds, pipeline traces, EPP weights visible
C43 | Reporting & CSV/PDF Export | Analytics | 5 | Medium | 15-20 | P1 | Not Started | Export all metrics, learner progress, coaching activity
C44 | Lesson Impact Preview | Platform | 5 | Medium | 15-20 | P2 | Not Started | Dry-run: what happens to paths if we add/remove a lesson

## Timeline
Phase | Deliverable | Week Start | Week End | Milestone | Gate / Review
1 | Data Model & Taxonomy Analysis | 1 | 2 | Data model documented
1 | EPP Integration Architecture | 2 | 3
1 | Schema Extensions & DB Optimization | 3 | 4 | Database ready | Phase 1 Review
2 | EPP Parser & Profile Engine | 5 | 8 | First profiles generated
2 | Motivation + Learning Style + Tension Pairs | 8 | 10
2 | Batch Profiling & Feedback Loop | 10 | 11 | 400+ profiles complete | Phase 2 Review
3 | AI Content Tagging Pipeline | 5 | 8 | Pipeline operational
3 | Confidence Gating & Review Queue | 8 | 10
3 | Semantic Search & Bulk Processing | 10 | 12 | 90 lessons tagged | Phase 3 Review
4 | Matching Algorithm & Sequencing | 13 | 16 | First paths generated
4 | Coach Workspace & Curation Tools | 16 | 19 | Coaches can edit paths
4 | Curator AI Copilot & Compatibility | 19 | 21 | Full coach toolkit | Phase 4 Review
5 | HR Dashboard & Analytics | 22 | 25 | Dashboard live
5 | Reassessment Engine & Passive Signals | 25 | 27 | Adaptation loop closed
5 | AI Companion & Reporting | 27 | 30 | Full system operational | Final Review & Handoff

## Success Metrics
Metric | Stakeholder | Target | Measurement Method | Phase Available | Current Baseline
Path Relevance Score | Product | >70/100 avg match | AI scoring algorithm output | Phase 4 | N/A (no personalization)
Discovery Phase Completion | Product | >60% of learners | Learner progress tracking | Phase 4 | N/A
Engagement Lift (saves/ratings) | Product | >25% increase | Compare pre/post CoachAI | Phase 5 | Current backpack/rating rates
Profile Accuracy | Learner | >85% no 'not like me' | Feedback button tracking | Phase 2 | N/A
Coach Time Savings | Coach | 70% reduction in path planning | Coach survey + task time tracking | Phase 4 | Current hours per learner
Coach Override Rate | Coach | 10-30% (healthy range) | Override audit trail | Phase 4 | 100% (fully manual)
Cohort Progression Rate | HR | >50% active in 90 days | Phase tracking dashboard | Phase 5 | Current completion rates
Content Utilization | HR | >80% of library matched | Content gap analysis | Phase 3 | Unknown
EPP Dimension Coverage | HR | >90% dimensions addressed | Trait mapping analysis | Phase 4 | 0% (no trait mapping)
Reassessment Drift | HR | Measurable change at 90 days | Quarterly EPP comparison | Phase 5 | No reassessments
Content Tag Confidence | Platform | >75% auto-approved | Confidence gating stats | Phase 3 | N/A
System Uptime | Platform | 99.5% | Monitoring | Phase 1+ | N/A

## Risks
ID | Risk | Likelihood | Impact | Mitigation | Owner | Status
R01 | EPP data quality varies across learners | Medium | Medium | Confidence scoring; fallback to Q&A-only profiling | ThoughtWire | Open
R02 | Content library too small for diverse matching | Low | High | Content gap analysis identifies where new content needed | MyNextory | Open
R03 | Coaches resist AI recommendations | Medium | Medium | Override tools preserve autonomy; AI positioned as assistant | Joint | Open
R04 | Learner privacy concerns with personality data | Medium | High | Data stays in MyNextory infra; consent-based; no external sharing | MyNextory | Open
R05 | AI errors in content tagging | Low | Medium | Multi-pass confidence + human review queue before impact | ThoughtWire | Open
R06 | Assessment fatigue from reassessments | Low | Low | Mini-assessments (3-5 Qs); passive signals reduce explicit asks | Joint | Open
R07 | Integration complexity with existing LMS | Medium | Medium | Layered architecture — additive, not replacement | ThoughtWire | Open
R08 | Scope creep across phases | Medium | Medium | Phase gates with explicit review before proceeding | Joint | Open